## IT DEVEL (hidden)
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | DATAGATE DEVELOPMENT
Enter Company Name in cell B2.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  | Project Start: |  | 2019-06-01
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 0 |  |  |  | 2019-05-20 | [6 empty] | 2019-05-27 | [6 empty] | 2019-06-03 | [6 empty] | 2019-06-10 | [6 empty] | 2019-06-17 | [6 empty] | 2019-06-24 | [6 empty] | 2019-07-01 | [6 empty] | 2019-07-08 | [6 empty] | 2019-07-15 | [6 empty] | 2019-07-22 | [6 empty] | 2019-07-29 | [6 empty] | 2019-08-05 | [6 empty] | 2019-08-12 | [6 empty] | 2019-08-19 | [6 empty] | 2019-08-26 | [6 empty] | 2019-09-02 | [6 empty] | 2019-09-09 | [6 empty] | 2019-09-16 | [6 empty] | 2019-09-23 | [6 empty] | 2019-09-30 | [6 empty] | 2019-10-07 | [6 empty] | 2019-10-14 | [6 empty] | 2019-10-21 | [6 empty] | 2019-10-28 | [6 empty] | 2019-11-04 | [6 empty] | 2019-11-11 | [6 empty] | 2019-11-18 | [6 empty] | 2019-11-25 | [6 empty] | 2019-12-02 | [6 empty] | 2019-12-09 | [6 empty] | 2019-12-16 | [6 empty] | 2019-12-23 | [6 empty] | 2019-12-30 | [6 empty] | 2020-01-06
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2019-05-20 to 2020-01-12
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | N DAYS | END | DAYS | time axis 2019-05-20 to 2020-01-12
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | DATABASE MODULES
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Development |  | 80% | 2019-06-01 | 20 | 2019-06-21 | 21
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Production |  |  | 2019-06-21 | 10 | 2019-07-01 | 11
| Validation |  |  | 2019-07-01 | 15 | 2019-07-16 | 16
| Release |  |  | 2019-07-16 | 15 | 2019-07-31 | 16
Creation of DATAGATE application
Project
Environment setup
Development
Environment setup
Creation of user login
Creation of
Task 5
Task 5
Sample phase title block | Phase 3 Title
Task 1
Task 2
Task 3
Task 4
Task 5
Sample phase title block | Phase 4 Title
| Task 1 |  |  | date |  | date | #VALUE!
| Task 2 |  |  | date |  | date | #VALUE!
| Task 3 |  |  | date |  | date | #VALUE!
| Task 4 |  |  | date |  | date | #VALUE!
| Task 5 |  |  | date |  | date | #VALUE!
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one

## 00. DATAGATE MODULES
BASIC MODULES
Define Architecture and instruments needed | Log-in | Departments views
Define global scope | Define different user settings by using role based authorization | Define main scope of each page
Define global architecture, sitemap, content | Create general views with common data access | Create Aum View:possibility to filter for date, fund, etc
Define languages for Front, back, reporting, libraries needed etc | Assess security | Create Fund view with all data and registration/update for shareclasses, sf, fund, companies and agreements
Define Security | Define log system and bug tracking
Define versioning
Define backup
Set up developer tools: server , software etc

## 01. DEFINE ARCHITECTURE
DEFINE ARCHITECTURE
Define Architecture and instruments needed | Languages | Security | Versioning | Backup | Developer tools | Testing and Deployment
Define global scope | Front - JavaScript Rest API - Node, React | Network, switch, router | GIT to track changes | 3, 2, 1 - 3 copies of data, 2 copies on different storage,one copy offsite | Server - MS SQL Server | Docker
Define global architecture, sitemap, content | Back - C# .NetCore | System | Github profile | Cloud | Software - Visual Studio, VS Code, Resharper, StarUml
Define languages for Front, back, reporting, libraries needed etc | Reporting Standard - VBA (existing) Dashboards Ad hoc??? | Web - SQL Injection, Cross site scripting (XSS), Windows Application Firewall (WAF) |  | Remote Desktop Connection, SQL Server | JasperSoft
Define Security | Database - SQL with robust approach | Wireless Authentication-WEP;WPA/WPA2
Define versioning
Define backup
Set up developer tools: server , software etc
Testing and Deployment

## 01A. SITEMAP
SITEMAP
Homepage | Login | About | Products & Services
| Authentfication | Contact | StatPro, Allocare
| Authorization - OAuth 2.0 | Partners | Reporting
| Authorization Stage 1 - Role Choice |  | Controls
Authorization Stage 2 - Get Permissions
Authorization Stage 3 - Paid For Modules

## 02. LOGIN
LOGIN
Log-in | Security | Log System
Define different user settings by using role based authorization | Login Controls | Nlog - Nuget
Create general views with common data access | Secure Sockets Layer
Assess security
Define log system and bug tracking

## 02A. LOGIN ROLES
LOGIN ROLES
Admin | Risk | Legal | Compliance | Investment | Special
Public Access | Public Access | Public Access | Public Access | Public Access | Legal SubFund Access
Admin Access | Risk Access | Legal Access | Compliance Access | Investment Access

## 02B. ACCESS - PERMISSIONS
PERMISSIONS-VIEWS
Public Access | Admin Access | Legal Access | Legal SubFund Access | Risk Access | Compliance Access | Investment Access | Verification Access
ViewCalendar | CRUD Permission |  | CanAddNewSubFund | CanPerformRiskControl |  |  | ConfirmAction
ConsultReports | CRUD User
ViewProjects | CRUD RoleUser
CanReadUsers - list

## 02C. USERS PERMISSIONS
USERS | ROLE | PERMISSIONS
1. Luigi | UserAdmin | Public, Admin, Legal SubFund, Verification
2. Fabio | UserAdmin
3. Marco
4. Pietro
5. Andrea
6. Oscar
7.Sabrina
8. Zita
9. Chantal
10
11
12
13
14
15

## 03. SOFTWARE ARCHITECTURE
SOFTWARE ARCHITECTURE
Requirements | Design | Patterns | Login | Features
| SOLID |  | Roles, Permissions | Refresh Claims???
| MVC |  |  | Keep track of user logs

## DETAIL DB MODULES
BASIC MODULES | [5 empty] | RISK MODULES | [5 empty] | OTHER MODULES
Shareclass Subfund Fund | Shareclasses AUM, subred NAV | Companies & Agreements | Fees | Portfolios with Asset details | Transactions | CREDIT RISK | LIQUIDITY RISK | MARKET RISK | INVESTMENT R. OVERSIGHT | COUNTERPARTY RISK | OPERATIONAL RISK | Performance Analysis | Performance Analysis (Contribution) | GPM lines RISK and Perf monitoring | COMPLIANCE | New Project SET-UP
This module contains all the registry of share classes, sub-funds and funds. Historic values and all relative domain tables(eg.currency, country) | This module collects every day the shareclasses AuM, subred and NAV | This module contains all the service agreements and relative codes. Plus a table of companies and contacts | This module contains all the fee table and historic values | This module collects all asset registry, all the position at nav date and relative domain and mapping tables | This module contains all the transaction for each portoflio | This module is created for credit risk analysis containing all the function/stored procedure for the model and analysis | This module contains all the function/storede procedure useful for liquidity risk monitoring | This module allows to store VaR data and Commitment coming from 3rd parties (in the future will be possbile to calculate it with proprietary models) | The scope of this module is to be able to imlement the investment restrictions rules (prospectus, low etc) and be able to internally perform the activity | This module contains the stored procedure and functions to be used for colaculating the counterparty risk (Σ pos>0 /nav) | In this module, function, stored procedure and table allow to keep history of oiperational risk measures (nav delay, nav error etc) | This module is created to perform the performacne analysis and calcualtion (based on shares prices) | This module is created to perform the performacne analysis thanks to transactions and reconciliate with performance calculation | This module inherits all the functions, stored procedures, and tables used for ptf, and applies the same to GPM lines | This module can leverage the basic module to have more information collected (AML/Compliance point of view) | This module is specific to create centralization project setup
tb_shareclass | tb_share_price | tb_service_agreements | tb_fees | tb_dom_asset_subtype | tb_transactions | fn_average_rating | fn_avg_volume
tb_subfund |  | tb_dom_service_type | tb_dom_fees | tb_dom_asset_type | tb_dom_transactions | fn_min_rating
tb_fund |  | tb_companies | b_dom_fees_type | tb_map_asset_subtype |  | fn_portoflio_rating(date)
tb_calendar
tb_map_sf_sc
tb_map_f_sf
tb_map_currency_country |  |  |  | tb_bond
tb_bond_values
tb_dom_iso_currencies |  |  |  | tb_countries_ratings
tb_dom_investor_type |  |  |  | tb_equities
tb_dom_share_type |  |  |  | tb_equities_values
tb_dom_iso_countries
tb_dom_macro_type |  |  |  | tb_derivatives
tb_dom_accounting_code |  |  |  | tb_target funds
tb_dom_share_status |  |  |  | tb_dom_target_fund_type
tb_dom_fund_status
tb_dom_sf_status |  |  |  | tb_rating
tb_dom_global_exposure |  |  |  | tb_dom_rating
tb_dom_calendar_type |  |  |  | tb_dom_economic_sector
tb_dom_nav_frequency
tb_dom_calculation_date
tb_dom_valuation_date
tb_dom_derivatives
tb_dom_deriv_exposure
tb_dom_legal_form
tB_dom_legal_type
tB_dom_legal_subtype
tb_dom_share_type
Note on E7: Author: ●Entity code (eg share) ●Fee code (link to dom fee) ●Fee start date ●Fee end date

## MODULE-ACTIVITY MATRIX
|  | BASIC MODULES | [5 empty] | RISK MODULES | [5 empty] | OTHER MODULES
|  | Shareclass Subfund Fund | Shareclasses AUM, subred NAV | Companies & Agreements | Fees | Portfolios with Asset details | Transactions | CREDIT RISK | LIQUIDITY RISK | MARKET RISK | INVESTMENT R. OVERSIGHT | COUNTERPARTY RISK | OPERATIONAL RISK | Performance Analysis | Performance Analysis (Contribution) | GPM lines RISK and Perf monitoring | COMPLIANCE | New Project SET-UP
ACTIVITIES | DEP | Shareclass Subfund Fund | Shareclasses AUM, subred NAV | Companies & Agreements | Fees | Portfolios with Asset details |  | CREDIT RISK | LIQUIDITY RISK | MARKET RISK | INVESTMENT R. OVERSIGHT | COUNTERPARTY RISK | OPERATIONAL RISK | Performance Analysis (Contribution) | GPM lines RISK and Perf monitoring | GPM lines RISK and Perf monitoring | COMPLIANCE | New Project SET-UP | 0
|  | 41 | 41 | 18 | 16 | 26 | 1 | 12 | 8 | 13 | 8 | 5 | 6 | 1 | 0 | 0 | 0 | 0 | 0
NEW Project Setup | ALL | x | x | x
AUM Report | ALL | x | x
Rating Allocation | RISK | x | x |  |  | x |  | x
Fund credit risk | RISK | x | x |  |  | x |  | x
Spread allocation | RISK | x | x |  |  | x |  | x
Bond Specifics | RISK | x | x |  |  | x |  | x
Bond Classification | RISK | x | x |  |  | x |  | x
Asset liquidity risk | RISK | x | x |  |  | x |  |  | x
Funding Liquidity risk | RISK | x | x |  |  | x |  |  | x
VaR storage (Via serv prov) | RISK | x | x |  |  | x |  |  |  | x
Backtest (Via serv prov) | RISK | x | x |  |  | x |  |  |  | x
Stress Test (Via serv prov) | RISK | x | x |  |  | x |  |  |  | x
UCTIS Leverage | RISK | x | x |  |  | x |  |  |  | x
UCTIS Commitment | RISK | x | x |  |  | x |  |  |  | x
AIF Leverage | RISK | x | x |  |  | x |  |  |  | x
EPT/EMT (Via serv prov) | RISK | x | x |  |  | x |  | x | x | x | x | x
AIFMD Report | RISK | x | x |  |  | x
CSSF Risk Report | RISK | x | x |  |  | x |  | x | x | x | x | x
Eligibilty | RISK | x | x |  |  | x |  |  |  |  | x
Investment Restriction Monitoring | RISK | x | x |  | x | x |  | x | x | x | x | x
Breach monitoring | RISK | x | x |  |  | x |  | x | x | x | x | x | x
Stale Price Monitoring | RISK | x | x |  |  | x
SRRI | RISK | x | x |  |  | x |  |  |  | x |  |  | TBD
Hedging SC monitoring | RISK | x | x | TBD |  | TBD | [6 empty] | TBD
Manco Fees | RISK | x | x | x | x | TBD
TER | RISK | x | x | x | x | TBD
Performance Fees | RISK | x | x | x | x | TBD | [7 empty] | x
Ongoing Charges | RISK | x | x | x | x | TBD
Trailer Fees | RISK | x | x | x | x | TBD
Othes Fees | RISK | x | x | x | x | TBD
Global Fees | RISK | x | x | x | x | TBD
Risk Fee | RISK | x | x | x | x | TBD
KPI | RISK | x | x | x | x | TBD | [6 empty] | x
RSA | RISK | x | x | x | x | TBD | [6 empty] | x
Board Pack Risk Report | RISK | x | x | x | x | x |  | x | x | x | x | x | x
Solvency Report (Via serv prov) | RISK | x | x | x | TBD | x |  | x | TBD | TBD | x | TBD
KIID Report | RISK | x | x | x | x
Factsheet Report | RISK | x | x | x | x | x
Overshight NAV | RISK | x | x | x | x | x | [6 empty] | x
PTR | ALL | x | x | x |  |  | x
Subfund statistics report | ALL | x | x | x | x | x | TBD | x | x | x | x |  | x

## MODULES DEPENDENCES
OTHER MODULES
|  |  |  | Performance Analysis | OTHER MODULES |  | OTHER MODULES
|  |  |  | BASIC MODULES | Performance Analysis (Contribution) |  | GPM lines RISK and Perf monitoring
|  |  |  | Transactions | RISK MODULES
BASIC MODULES | BASIC MODULES |  | BASIC MODULES | BASIC MODULES | MARKET RISK
Shareclass Subfund Fund | Companies & Agreements |  | Shareclasses AUM, subred NAV | Portfolios with Asset details | RISK MODULES |  | RISK MODULES | RISK MODULES
[5 empty] | LIQUIDITY RISK |  | INVESTMENT R. OVERSIGHT | OPERATIONAL RISK
|  | OTHER MODULES |  |  | RISK MODULES
|  | COMPLIANCE |  |  | CREDIT RISK
RISK MODULES
COUNTERPARTY RISK
|  |  |  | BASIC MODULES |  | OTHER MODULES
|  |  |  | Fees |  | New Project SET-UP